## Tasks Completed
Task Number | Tasks | Owner | Completion Dates | Notes
1 | Get 100 phage EM images per class. Three clases in total; therefore 300 phage EM images overall. | Alexandra Rodier | 2024-03-22 | Most phages in dataset are not pre-labeled. Used the ones that were pre-labeled with their morphological family. Had to go into each phage's individual data page to check if phage EM image was present along with the nm scale; therefore, also had to download the images one-by-one.
2 | Since phage EM images varied in size, decide on a size to use resize all the images to. | Alexandra Rodier | 2024-03-26 | Originally chose 1024 x 1024; however, computer would sometimes crash when the models were running. Therefore, changed to size 512 x 512, which fixed this issue.
3 | Build and test multiple CNN models, including one self built model and then other models using a pre-loaded base model with custom layers on top | Alexandra Rodier | 2024-03-26 | These models had a lower test accuracy than desired and expected, ranging from 45% to 75% depending on the model.
4 | Extract a single phage and the nm scale from each original phage EM image | Alexandra Rodier | 2024-03-29 | Used the Segment Anything website, which allows for each object to be saved as an image file with a transparent background. Therefore, the phage (file name ends in "A") and the scale (file name ends in "B") are saved as separate images but with the attached file name number (Example: "1A" and "1B").
5 | For each original phage EM image: Combine the extracted phage and the associated nm scale together into a single image | Alexandra Rodier | 2024-03-29 | Had the phage placed on the top and scale placed on the bottom with both of them centered within that respective zone. The width of the image is based on which component had the larger width. Placed light lilac color around empty zones of image.
6 | Resized the new, adjusted phage EM images to 512 x 512 | Alexandra Rodier | 2024-03-29 | For images that had a width or height greater than 512, they were compressed to this size, while a width or height less than 512, light lilac color was placed around the inital image.
7 | Test the new, adjusted phage EM images on the already created models | Alexandra Rodier | 2024-03-29 | Higher test accuracy than previously.
8 | Additional model grid searches using the new, adjusted phage EM dataset | Alexandra Rodier | 2024-04-12 | For example - Best Batch Size: ResNet-152: 16 VGG19: 32
9 | Obtain test accuraries for final models | Alexandra Rodier | 2024-04-13 | Best model is with ResNet-152 as the base model with a test accuracy of 93.75%.
10 | See if any additional model changes can make best model's test accuracy increase | Alexandra Rodier | 2024-04-13 | Either remained the same as 93.75% or decreased.
11 | Investigate confusion matrix for best model and determine reasoning for any misclassifications | Alexandra Rodier | 2024-04-14 | Three Myoviridaes phage EM images misclassified as Siphoviridaes. Model not having enough training on Myoviridae phages with long tail lengths.
12 | Written Report | Alexandra Rodier | 2024-04-26
13 | Video | Alexandra Rodier | 2024-04-27